## RISK REGISTER
RISK ID | RISK DESCRIPTION | CATEGORY | PROBABILITY (1-5) | IMPACT (1-5) | RISK SCORE | RISK LEVEL | OWNER | STATUS | MITIGATION PLAN | DUE DATE | OVER DUE?
R-01 | Designer unavailable | Resource | 4 | 5 | 20 | CRITICAL | Asha | Open | Arrange backup designer | 2026-10-18 | On Track
R-02 | Budget overrun >10% | Budget | 3 | 5 | 15 | CRITICAL | Ravi | In Progress | Daily cost tracking | 2026-10-19 | On Track
R-03 | Client feedback delay | Schedule | 5 | 4 | 20 | CRITICAL | Neha | Open | Send reminder + buffer | 2026-10-20 | On Track
R-04 | Tool license expiry | Technical | 2 | 2 | 4 | MEDIUM | Kiran | Mitigated | Renew license early | 2026-10-12 | Due Today
R-05 | QA resource sick | Resource | 3 | 3 | 9 | HIGH | Swetha | Open | Cross-train team member | 2026-10-22 | On Track
R-06 | Scope creep by client | Scope | 4 | 4 | 16 | CRITICAL | Asha | Open | Freeze scope document | 2026-10-23 | On Track
R-07 | Server downtime | Technical | 2 | 5 | 10 | HIGH | Ravi | Closed | Use backup server | 2026-10-24 | Completed
R-08 | Vendor payment delay | Budget | 3 | 2 | 6 | MEDIUM | Neha | In Progress | Follow up with finance | 2026-10-25 | On Track
Formulas:
OVER DUE? = IF([STATUS]="Closed","Completed",IF([DUE DATE]<TODAY(),"OVERDUE",IF([DUE DATE]=TODAY(),"Due Today","On Track")))

## RACI MATRIX
TASK | Asha-PM | Ravi-Dev | Neha-Design | Kiran-QA | Rajesh-Client
Req Gathering | A | C | C | C | R
UI Design | A | I | R | C | C
Budget Approval | A | I | I | I | R
Development | A | R | C | C | I
Testing | A | C | I | R | I
Risk Monitoring | R | C | C | C | A
Client Demo | A | R | R | C | I
Go-Live | A | R | C | R | I
LEGEND
R = Responsible (Does the work)
A = Accountable (Final Owner - Only ONE per task)
C = Consulted (2-way discussion before work)
I = Informed (1-way update after work)